## Pre-filled Starter Sheet
Purpose Conveys the scope of various tasks that need to be coordinated to build and launch the product/feature | What is the task? Based on the purpose, select the appropriate from the drop-down | Who is the task owner? Does the following to finish task: 1. Schedule and run meetings 2. Gather feedback and share updates 3. Follow-up with stakeholders | Whose involvement is needed to accomplish the task ? Please select one from the drop-down list of your identified stakeholders | What is their role? Select the stakeholder's role from the drop-down. Note: 'Scrum Team' role is applicable to stakeholder 'Scrum Team' only | By when, does the task need to be completed? Select milestone keeping in mind nature of the task,downstream effects of delaying task
Evangelize internally | Setup PRD review meeting to receive feedback | Product Manager | Head of Product | Approver (Has the final say on a specific aspect of the project) | Set a target week
|  |  | Impacted Product Managers | Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to share MVP scope and walk-through design to gather feedback |  | Cross-functional Stakeholders | Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to kickoff project with the scrum team |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Involve legal and compliance | Setup meeting to review MVP scope and identify possible legal updates.e.g Terms of Use and Privacy Policy | Product Manager | Legal and Compliance | Contributors (Consulted for their opinions or expertise to help with project decisions) | Set a target week
| Get feedback on previously identified legal areas to update. e.g Terms of Use and Privacy Policy |  | Legal and Compliance | Contributors (Consulted for their opinions or expertise to help with project decisions) | Before project's final sprint starts
Incorporate stakeholders feedback | Discuss the prioritized feedback received from stakeholders to update scope and design | Product Manager | Product Designer | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
Initiate and maintain feedback loop | Create a project-specific communication channel (in Slack etc) to share insights from customer meetings/usability tests/data analysis | Product Manager | All except Legal and Compliance | Informed (No authority over the decisions and need to stay updated on the progress since it impacts their own work) | Before project's sprint 0 starts
Plan development work | Setup solution feasibility discussions to understand the work involved/identify inter-dependencies and potential risks | Product Manager | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 0 starts
| Identify critical spike and engineering design work to complete prior to product/feature development | Engineering Lead
Manage product/feature testing | Share and review the project's test strategy | QA | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 1 starts
Setup analytics tracking | Review analytics tracking requirements | Data Analyst | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before project's sprint 1 starts
Prepare for every sprint | Create tickets for each sprint based on the test strategy | QA | Scrum Team | Scrum Team (Involved directly in product development efforts) | Before each sprint starts
| Create tickets for each sprint based on the analytics tracking requirements | Data Analyst
| Finalize user-stories and design to add for each sprint | Product Manager
Coordinate product/feature launch | Discuss launch plan and targeted timelines to align with development cycle | Product Marketing | Product Manager | Contributors (Consulted for their opinions or expertise to help with project decisions) | Before project's sprint 1 starts
| Identify the support material that needs to be prepared and targeted timelines to align with development cycle | Customer Service | Product Manager | Contributors (Consulted for their opinions or expertise to help with project decisions) | Before project's sprint 1 starts
Communicate project progress | Share project's progress and highlight any risks (setup recurring meeting/send email/ share via team's channel e.g Slack) | Product Manager | Head of Product/Impacted Product Managers/Cross-functional stakeholders | Informed (No authority over the decisions and need to stay updated on the progress since it impacts their own work) | Before each sprint ends
Receive product/feature sign-off | Setup meeting to demo the feature and conduct end-to-end feature testing to identify bugs and receive feedback | Product Manager | Head of Product | Approver (Has the final say on a specific aspect of the project) | Before project's last sprint ends
|  |  | Impacted Product Managers | Contributors (Consulted for their opinions or expertise to help with project decisions)
|  |  | Cross-functional Stakeholders | Contributors (Consulted for their opinions or expertise to help with project decisions)

## Help Information
Stakeholders identified for the project
Head of Product
Impacted Product Managers (Your product/feature impact the product/feature they mange directly or indirectly)
Cross-functional Stakeholders (Representation from these areas: Customer Service, Marketing (includes Product Marketing) and Operations )
Scrum Team (Mentioned here)
Legal and Compliance
Customer Service